## Read Me
Teen Leaders of America — Deliverables Tracking System
Purpose
This workbook operationalizes the contract deliverables in Table 9 (Program Design Deliverables) into a monthly tracking system with owners, data sources, and status flags, so the program can be managed proactively and reported on accurately every month and at year-end.
Program year used in this workbook | September 2026 – August 2027 (school-year aligned out-of-school-time calendar). If your actual contract year runs on a different cycle (e.g., July–June, or calendar year), relabel the month headers on the Tracker and Timeline tabs — the formulas do not depend on the specific month names.
Where to enter your enrollment number | Dashboard tab, cell C4 (yellow fill). Every percentage-based deliverable on the Tracker recalculates automatically off this number.
Where to enter monthly data | Deliverable Tracker tab — yellow cells only. Everything else (percentages, status flags, YTD totals) is a formula and will update itself.
Where to see the current status | Dashboard tab — auto-populated summary of every deliverable, color-coded On Track / At Risk / Off Track.
Where to plan the year | Annual Timeline & Owners tab — month-by-month action calendar showing exactly what should be happening and who is responsible.
What to send funders/leadership monthly | Monthly Report Template tab — pulls live from the Tracker, just select the reporting month.
Color key used throughout | Yellow = enter data here. Navy header = section title. Green status = On Track. Amber = At Risk. Red = Off Track.

## Dashboard
Program Dashboard — Live Status
Total Enrolled / Participating Youth (enter here) |  | → | 100 | This single cell drives every percentage below
Reporting month (for the header on printouts) |  |  | Jan-27
Deliverable | Target | Current Actual | % of Target | Status | Owner
Workforce/Personality Assessments | 50% of youth (annual) | 0 | 0% | Off Track | Program Coordinator
Academic Support (weekly) | 75% of youth engaged monthly | 0 | 0% | Off Track | Academic Coordinator
Workforce Development Workshops (monthly) | 75% of youth/month | 0 | 0% | Off Track | Workforce Dev. Lead
Workforce Development Stipends | 30% of youth (annual) | 0 | 0% | Off Track | Program Director
College Exploration (monthly) | 75% of youth/month | 0 | 0% | Off Track | College Access Coord.
Industry Certifications | Up to 20 youth (annual) | 0 | 0% | Off Track | Workforce Dev. Lead
Service-Learning Activities | ≥3 per program year | 0 | 0% | Off Track | Program Coordinator
Family Engagement Activities | ≥3 per program year | 0 | 0% | Off Track | Family Engagement Lead
Social/Enrichment Activities | ≥2 per month | 0 | 0% | Off Track | Program Coordinator
Note on D3: Enter the current total number of enrolled/participating youth for the program year. All % targets below recalculate off this number.

## Deliverable Tracker
Deliverable Tracker — Monthly Data Entry
Enter data only in yellow cells. All percentages, YTD totals, and status flags calculate automatically.
Category | Deliverable (Contract Language) | Metric Type | Target | Frequency | Owner | Data Source / Tracking Method | Enrolled (linked) | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Current Actual | % of Target | Status
Assessments | At least 50% of participating youth will complete a workforce or personality development assessment (e.g., Myers-Briggs, Pelocity) per program year. | Cumulative Pct | 50% | Annual | Program Coordinator | Assessment completion log / case management system | 100 | [12 empty] | 0 | 0% | Off Track
Academic Support | At least 75% of participating youth will receive academic support once per week during out-of-school-time programming. | Monthly Pct | 75% | Monthly | Academic Coordinator | Weekly sign-in sheets / tutoring log | 100 | [12 empty] | 0 | 0% | Off Track
Workforce Development Workshops | At least 75% of participating youth will participate in workforce development workshops once per month during out-of-school-time programming. | Monthly Pct | 75% | Monthly | Workforce Dev. Lead | Workshop attendance sign-in sheets | 100 | [12 empty] | 0 | 0% | Off Track
Workforce Development Stipends | At least 30% of participating youth will earn a financial stipend during the program year. | Cumulative Pct | 30% | Annual | Program Director | Stipend disbursement / finance records | 100 | [12 empty] | 0 | 0% | Off Track
College Exploration | At least 75% of participating youth will participate in college exploration activities once per month during out-of-school-time programming. | Monthly Pct | 75% | Monthly | College Access Coordinator | College exploration attendance log | 100 | [12 empty] | 0 | 0% | Off Track
Industry Certifications | Up to 20 students will earn industry certifications per program year. | Cumulative Count | 20 | Annual | Workforce Dev. Lead | Certification issuance records | 100 | [12 empty] | 0 | 0% | Off Track
Service Learning | Teen Leaders of America will offer at least 3 service-learning activities per program year. | Cumulative Activity Count | 3 | Annual | Program Coordinator | Activity calendar / event log | 100 | [12 empty] | 0 | 0% | Off Track
Family Engagement | Teen Leaders of America will offer at least 3 family engagement activities per program year. | Cumulative Activity Count | 3 | Annual | Family Engagement Lead | Activity calendar / sign-in sheets | 100 | [12 empty] | 0 | 0% | Off Track
Social/Enrichment | Teen Leaders of America will offer at least 2 social or enrichment activities once per month. | Monthly Activity Count | 2 | Monthly | Program Coordinator | Activity calendar / sign-in sheets | 100 | [12 empty] | 0 | 0% | Off Track
Note on U5: Enter the CUMULATIVE unduplicated number of youth who have completed the assessment as of each month (running total, not a monthly count).
Note on U6: Enter the number of unique youth who participated THAT MONTH. Current Actual shows the most recent month entered; % of Target compares it to enrollment.
Note on U7: Enter the number of unique youth who participated THAT MONTH. Current Actual shows the most recent month entered; % of Target compares it to enrollment.
Note on U8: Enter the CUMULATIVE unduplicated number of youth who have completed the assessment as of each month (running total, not a monthly count).
Note on U9: Enter the number of unique youth who participated THAT MONTH. Current Actual shows the most recent month entered; % of Target compares it to enrollment.
Note on U10: Enter the CUMULATIVE number of youth who have earned a certification as of each month (running total).
Note on U11: Enter the NUMBER OF ACTIVITIES held in each month (e.g., 1 in the month it occurred). Current Actual sums the year to date.
Note on U12: Enter the NUMBER OF ACTIVITIES held in each month (e.g., 1 in the month it occurred). Current Actual sums the year to date.
Note on U13: Enter the number of activities held THAT MONTH. Current Actual shows the most recent month entered.

## Annual Timeline & Owners
Annual Timeline & Owners — What Should Be Happening Each Month
Program year: September 2026 – August 2027. Relabel months if your contract year differs.
Month | Action Items | Owner | Data / Reporting Due
Sep-26 | • Program kickoff: confirm enrollment roster and record total enrolled count in Dashboard!D3 • Launch workforce/personality assessments (Meyers-Briggs/Pelocity) with new cohort • Begin weekly academic support sessions • Hold Month 1 workforce development workshop • Hold Month 1 college exploration session • Hold 2 social/enrichment activities • Set up attendance/sign-in systems for all activity types | Program Director | Baseline enrollment confirmed; Sept sign-in sheets collected
Oct-26 | • Continue weekly academic support • Hold Month 2 workforce development workshop • Hold Month 2 college exploration session • Hold 2 social/enrichment activities • Plan first service-learning activity (target: complete by Dec) • Continue assessment completion push toward 50% annual target | Program Coordinator | Oct data entered in Tracker; 1st monthly internal review
Nov-26 | • Continue weekly academic support • Hold Month 3 workforce development workshop • Hold Month 3 college exploration session • Hold 2 social/enrichment activities • Deliver 1st family engagement activity (target: complete by Dec) • Mid-checkpoint: review assessment completion % vs 50% target | Program Coordinator / Family Engagement Lead | Nov data entered; Board/funder update if required
Dec-26 | • Continue weekly academic support • Hold Month 4 workforce development workshop • Hold Month 4 college exploration session • Hold 2 social/enrichment activities • Complete 1st service-learning activity • Quarter 1 report: compile Sep-Nov actuals into Monthly Report Template | Program Director | Q1 report finalized and shared with funder/board
Jan-27 | • Continue weekly academic support • Hold Month 5 workforce development workshop • Hold Month 5 college exploration session • Hold 2 social/enrichment activities • Identify first cohort ready for industry certification exams • Begin stipend eligibility tracking toward 30% annual target | Workforce Dev. Lead | Jan data entered; certification pipeline list started
Feb-27 | • Continue weekly academic support • Hold Month 6 workforce development workshop (mid-year point) • Hold Month 6 college exploration session • Hold 2 social/enrichment activities • Complete 2nd family engagement activity • Mid-year formal review: compare all deliverables vs. annual pace | Program Director | Mid-year review meeting with leadership
Mar-27 | • Continue weekly academic support • Hold Month 7 workforce development workshop • Hold Month 7 college exploration session • Hold 2 social/enrichment activities • First round of industry certification exams/completions • Disburse first workforce stipends | Workforce Dev. Lead / Program Director | Mar data entered; stipend disbursement records filed
Apr-27 | • Continue weekly academic support • Hold Month 8 workforce development workshop • Hold Month 8 college exploration session • Hold 2 social/enrichment activities • Q3 report: compile Jan-Mar actuals into Monthly Report Template • Review on-track deliverables and flag any at risk for corrective action | Program Coordinator | Q3 report finalized and shared with funder/board
May-27 | • Continue weekly academic support • Hold Month 9 workforce development workshop • Hold Month 9 college exploration session • Hold 2 social/enrichment activities • Complete 3rd service-learning activity (meets annual minimum of 3) • Continue stipend disbursements toward 30% target | Program Coordinator | May data entered; service-learning target status confirmed
Jun-27 | • Continue weekly academic support • Hold Month 10 workforce development workshop • Hold Month 10 college exploration session • Hold 2 social/enrichment activities • Complete 3rd family engagement activity (meets annual minimum of 3) • Second round of industry certification completions | Family Engagement Lead / Workforce Dev. Lead | Jun data entered; family engagement target status confirmed
Jul-27 | • Continue weekly academic support • Hold Month 11 workforce development workshop • Hold Month 11 college exploration session • Hold 2 social/enrichment activities • Final push on assessment completions (50% annual target) • Final push on stipend disbursements (30% annual target) | Program Director | Jul data entered; year-end gap analysis for any lagging deliverable
Aug-27 | • Final weekly academic support sessions of the program year • Hold Month 12 (final) workforce development workshop • Hold Month 12 (final) college exploration session • Hold 2 social/enrichment activities • Finalize all industry certifications (up to 20 target) • Year-end report: full Table 9 deliverables summary for funder • Begin planning next program year based on this year's results | Program Director | Annual report finalized; all 9 deliverables closed out

## Monthly Report Template
Monthly Deliverables Report
Reporting Month | Jan-27
(Set the reporting month on the Dashboard tab, cell D5 — this sheet updates automatically)
Total Enrolled / Participating Youth | 100
Deliverable | Contract Target | Current Actual | % of Target | Status | Owner
Workforce/Personality Assessments | Cumulative Pct — 50% | 0 | 0% | Off Track | Program Coordinator
Academic Support (weekly) | Monthly Pct — 75% | 0 | 0% | Off Track | Academic Coordinator
Workforce Development Workshops (monthly) | Monthly Pct — 75% | 0 | 0% | Off Track | Workforce Dev. Lead
Workforce Development Stipends | Cumulative Pct — 30% | 0 | 0% | Off Track | Program Director
College Exploration (monthly) | Monthly Pct — 75% | 0 | 0% | Off Track | College Access Coordinator
Industry Certifications | Cumulative Count — 2000% | 0 | 0% | Off Track | Workforce Dev. Lead
Service-Learning Activities | Cumulative Activity Count — 300% | 0 | 0% | Off Track | Program Coordinator
Family Engagement Activities | Cumulative Activity Count — 300% | 0 | 0% | Off Track | Family Engagement Lead
Social/Enrichment Activities | Monthly Activity Count — 200% | 0 | 0% | Off Track | Program Coordinator
Notes / Narrative for this reporting period (fill in before sending):